Tobacco Task Force Report

Cecil County Community Health Advisory Committee

January 21, 2010

The following summarizes progress of the Local Action Plan for the Local Public Health Tobacco Use Prevention and Cessation Program Grant FY 2010 after sustaining a $223,000 budget cut.  Activities in the grant’s school component were eliminated and activities in the community component were severely reduced.

Community

- Tobacco Task Force meetings were held on September 11 and November 6, 2009.  Two law enforcement subcommittee meetings were held as summarized in the enforcement section below.

- To date, 38 print media campaigns were implemented through educational materials, displays, flyers and community newsletters with an estimated 133,308 contacts; and 44 awareness campaigns educated 1,797 Cecil County residents about Tobacco Use Prevention and Cessation resources.

- To date, twelve “Community Volunteer Outreach Trainings” have been held training 110 volunteers who provided 2,140 one-to-one educational contacts in their communities about free tobacco cessation services offered by the Health Department.

- The Secondhand Smoke Program, “Care for Their Air”, addresses the issue of tobacco use and secondhand smoke, especially among pregnant women and families with young children.  Twenty secondhand smoke programs were completed educating 1,293 individuals to date.

- Six community organizations and churches were each awarded $500 mini-grants to conduct tobacco use prevention activities for the minority population in Cecil County:  Cokesbury United Methodist Church, River Rock Apostolic Faith Church, Generation Station Youth Center, Girl Scouts of the Chesapeake Bay, Girl Scouts Troop #20 for Rudy Park, and Haven House Drug Rehabilitation Shelter.

- A “Joining Together to Fight Cancer” Community Mini-grant Conference to address tobacco use prevention, featuring keynote speakers Drs. Cydney Teal and Irfan Hissamudin was held on August 3, 2009 at Union Hospital for 70 participants.

Cessation

- Due to budget reductions, the Nicotine Replacement and Chantix TM Program was eliminated.

- To date, 339 Cecil County residents received one-to-one consultations.

- To date, seven “Tools To Be Tobacco Free” cessation programs targeting pregnant women and parents with young children were completed, reaching 104 individuals.

Enforcement

- As a part of the Law Enforcement Subcommittee meeting on September 11, 2009, a Tobacco Compliance Check Training was held.  Law enforcement officers were trained on tobacco compliance check policies and report form documentation, and were updated on tobacco legislation.  Subcommittee members reviewed Community Tobacco Use Prevention Mini-grant applications and selected six mini-grants to award for FY2010.  On November 6, 2009, a Law Enforcement Subcommittee meeting was held to discuss tobacco vendor citations from FY 2009 that were reported to the Maryland Comptroller’s Office in September 2009.  The Maryland Comptroller’s Office held Administrative Hearings for the 11 tobacco vendors.  All vendors provided evidence of company policy, training and commitment for enforcing the prohibition of selling tobacco to minors, thus these cases were dismissed since they were considered a first offense.

- In FY 2010, six law enforcement agencies were contracted to provide tobacco vendor education and compliance checks: Cecil County Sheriff’s Office, Elkton Police Department, Maryland State Police Barrack F, Department of Natural Resources Police, North East Police Department, and Rising Sun Police Department.  Law enforcement activities will begin in Spring 2010.

  - In FY 2010, due to budget cuts, the Youth Tobacco Use Diversion Program (YTUDP) was not funded but continued as an in-kind program of the Neighborhood Youth Panel.  Community panel training concerning tobacco use prevention was held on July 23, 2009 for 23 participants.  A Pre-Quit program was provided for one youth tobacco offender referred from the program.

"Communities Putting Prevention to Work Grant"

  - Cecil and Frederick Counties were selected by Department of Health and Mental Hygiene’s Center of Health Promotion, Education & Tobacco Use Prevention to apply for “Communities Putting Prevention Work Grant” Category B from the Centers for Disease Control (CDC) to address tobacco use prevention and control through policy changes.  The competitive grant application for this project was submitted to CDC in November 2009; awards will  be made in February 2010.